## Project Plan
Week: | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6
Day: | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Date: | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Group Meetings
Project Kick-Off and Initial Research
Project Deliverables:
Project Initiation Document (PID)
Course (Lecturer) Briefing Document
Course (Student) Briefing Document
Website
Topic Specific Deliverables:
- Topic Summary and Objectives
- Presentation
- Presentation Recording and Transcript
- Additional Learning Material
Key:
Meetings
Project Work
Review
Interim Submission
Final Deadline

## Responsibilities
Project Item | Responsible
Project Initiation Document (PID) | M Towle & R Findlay
Meeting Minutes | R Findlay
Website | S Casas
Course (Lecturer) Briefing Document | M Towle
Course (Student) Briefing Document | M Towle
Individual Topic Content:
Topic 1: Managing Process Improvement Projects | S Almgren & A Loannidis
Topic 2: Managing New Product Development Projects | J Podschus & M Towle
Topic 3: Managing an International Project | S Casas & R Findlay

## Allocation of Days
Project Item | Working Days Budgeted
| Estimated | Actual
Group Meetings | 1 | 1
Project Kick-Off and Initial Research | 1 | 1.25
Project Initiation Document (PID) | 1 | 1.5
Course (Lecturer) Briefing Document | 0.25 | 0.25
Course (Student) Briefing Document | 0.25 | 0.25
Website | 1.5 | 1.75
Topic 1: Managing Process Improvement Projects
- Topic Summary and Objectives | 0.25 | 0.1
- Presentation | 3.5 | 3
- Presentation Recording and Transcript | 0.5 | 0.5
- Additional Learning Material | 0.75 | 0.5
Topic 2: Managing New Product Development Projects
- Topic Summary and Objectives | 0.25 | 0.1
- Presentation | 3.5 | 3.5
- Presentation Recording and Transcript | 0.5 | 0.4
- Additional Learning Material | 0.75 | 0.75
Topic 3: Managing an International Project
- Topic Summary and Objectives | 0.25 | 0.1
- Presentation | 3.5 | 3
- Presentation Recording and Transcript | 0.5 | 0.6
- Additional Learning Material | 0.75 | 0.75
Total: | 20 | 19.3

## Topic 1 Checksheet
Topic Name: Managing Process Improvement Projects
Date: 14th November 2016
Deliverables:
- Topic Summary and Objectives
- Presentation
- Presentation Recording and Transcript
- Additional Learning Material
Additional Notes:
Produced By:
S Almgren & A Loannidis
Reviewed By:
J Podschus
Approved By:
M Towle

## Topic 2 Checksheet
Topic Name: Managing New Product Development Projects
Date: 14th November 2016
Deliverables:
- Topic Summary and Objectives
- Presentation
- Presentation Recording and Transcript
- Additional Learning Material
Additional Notes:
Produced By:
J Podschus & M Towle
Reviewed By:
S Almgren
Approved By:
R Findlay

## Topic 3 Checksheet
Topic Name: Managing an International Project
Date: 14th November 2016
Deliverables:
- Topic Summary and Objectives
- Presentation
- Presentation Recording and Transcript
- Additional Learning Material
Additional Notes:
Produced By:
S Casas & R Findlay
Reviewed By:
J Podschus
Approved By:
M Towle